## Description of Inputs
Description of Inputs Required
Please do not modify the Functional Integration Plan template. If you have proposed changes, please talk to PMO for review.
Column | Please complete the following columns for your functional integration plan:
B | Owner | Name of task owner responsible for implementation
C | Task Focus | Functional area /high-level task focus
D | Task Description | Description of task or key milestone
E | Non-negotiable | If task is non-negotiable and must be implement, indicate "Y" for Yes or "N" for No
F | Start Date | Enter estimated start date of task
G | End Date | Enter estimated end date of task
H | Completion Date | Once task is completed, please enter date
M | Status | Use drop down to select status update according to legend (identifies status on dates identified)
P-S | Dependency Mgmt Plan | This is optional, but highly desirable to identify, communicate and get agreement with other
departments you have a dependency on to complete your work)
|  | Status Key / Legend: | G | On track | R | Escalation, assistance reqd
|  |  | Y | Potential delay, but no assist. reqd | C | Complete

## IT Infrastructure
IT M&A Work Plan
| Function: | IT Infrastructure |  |  |  | Status Key: |  | G | On track |  | R | Escalation, assistance reqd
| Lead: | Tony Quintus | [5 empty] | Y | Potential delay, but no assist. reqd |  | C | Complete
[9 empty] | Duration | Phase This Task Will Be Completed |  |  |  |  | Dependency Tracking
[10 empty] | 2012-09-01 | 2012-11-30 | YE 2012
Task | Owner | Task Focus | Task Description | Non- Neg (Y/N) | Timing | Start Date | Estimated End Date | Actual Date Complete | Estimated Days | Pre-Close to Day 1 | Phase 1: Days 2- 90 | Phase 2: Days 91+ | Status | Status Notes | Dependency on… (dept, person, vendor, etc) | Description of dependency | Date dependency needs to be delivered | Alignment complete (R, Y, G, C)
|  | Framework | Establish an Organizational Model |  | Evolving | 2012-09-01
|  | Framework | Dedicated Team: Director, PMs, BAs, Matrix of SMEs from Functional Areas |  | Evolving | 2012-09-01
|  | Framework | Business Person: responsible for all aspects of growth & identifies value points |  | Evolving | 2012-09-01
|  | Framework | Sales Operations Person: to preserve the value points & drive growth |  | Evolving | 2012-09-01
|  | Framework | Technical Person: preserve the keys to success, protect value points, customer focused |  | Evolving | 2012-09-01
|  | Framework | Define Principles & Guidelines |  | Evolving | 2012-09-01
|  | Framework | Establish Guiding Principles |  | Evolving | 2012-09-01
|  | Framework | Establish Core Tenants |  | Evolving | 2012-09-01
|  | Framework | Establish a Governance Model |  | Evolving | 2012-09-01
|  | Framework | Establish an Integration Council (benefits M&A and all project-based work) |  | Evolving | 2012-09-01
|  | Framework | Data Governance |  | Evolving | 2012-09-01
|  | Framework | Process Governance |  | Evolving | 2012-09-01
|  | Framework | Architectural Governance |  | Evolving | 2012-09-01
|  | Framework | PMO: |  | Evolving | 2012-09-01
|  | Framework | Issue & Risk Mgmt. |  | Evolving | 2012-09-01
|  | Framework | Measurement & Monitoring |  | Evolving | 2012-09-01
|  | Framework | Lessons Learned |  | Evolving | 2012-09-01
|  | Framework | Establish an Integration Mgmt. Office |  | Evolving | 2012-09-01
|  | Framework | Planning & Execution |  | Evolving | 2012-09-01
|  | Framework | Hardware, System, Data, & Processes |  | Evolving | 2012-09-01
|  | Framework | Coordinate X-Functional teams (includes service owners) |  | Evolving | 2012-09-01
|  | Framework | Integration Strategy Playbook: |  | Evolving | 2012-09-01
|  | Framework | Establish a functional playbook |  | Evolving | 2012-09-01
|  | Framework | Align on value points |  | Evolving | 2012-09-01
|  | Framework | Align "commits" to UL's Shared Services Model across the M&A Lifecycle |  | Evolving | 2012-09-01
|  | Framework | Identify Key Metrics |  | Evolving | 2012-09-01
|  | Framework | Track value points through the integration process |  | Evolving | 2012-09-01
|  | Framework | Tools, Templates, and Technology |  | Evolving | 2012-09-01
|  | Framework | Define an M&A Playbook for tracking all activities |  | Evolving | 2012-09-01
|  | Framework | Functional Integration Plan |  | Evolving | 2012-09-01
|  | Framework | Collaboration |  | Evolving | 2012-09-01
|  | Framework | Issue & Risk Mgmt. |  | Evolving | 2012-09-01
|  | Framework | CRM Integration Plan |  | Evolving | 2012-09-01
|  | Framework | Define Accelerator Tools |  | Evolving | 2012-09-01
1.1.0 |  | Due Dilligence | Management Office / Communication |  | Pre-Day 1 | 2012-09-01 | 2012-09-11 |  | 10 |  | X
1.1.1 |  | Due Dilligence | Determine if TSA is required and application impacts as a result |  | Pre-Day 1 | 2012-09-01 | 2012-09-02 |  | 1 |  | X
1.1.2 |  | Due Dilligence | Create M&A Council DD and Integration Planning Report |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
1.1.3 |  | Due Dilligence | Evaluate International Constraints for Day 1 Deliverables |  | Pre-Day 1 | 2012-09-01 | 2012-09-11 |  | 10 |  | X
1.1.4 |  | Due Dilligence | Create CIO Staff IT Due Dilligence Email and Report |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
1.1.5 |  | Due Dilligence | Evaluate legacy acquisition network for sustaining and scaling |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
1.1.6 |  | Due Dilligence | IT integration cost budget defined and approved |  | Pre-Day 1 | 2012-09-01 | 2012-09-01 |  | 0 | X | X
1.2.0 |  | Due Dilligence | Value Creation |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
1.2.1 |  | Due Dilligence | Analyze IT Financials of target |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
1.2.2 |  | Due Dilligence | Identify high level synergy opportunities |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
1.2.3 |  | Due Dilligence | Understand common baseline technologies for target industry |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
1.3.0 |  | Due Dilligence | Organization & Workforce |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
1.3.1 |  | Due Dilligence | Assess IT Organization |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
1.3.2 |  | Due Dilligence | Evaluate cultural considerations |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
1.3.3 |  | Due Dilligence | Create IT retention list |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
1.4.0 |  | Due Dilligence | Software & Vendor Management |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
1.4.1 |  | Due Dilligence | Review software licensing management & renewal process |  | Pre-Day 1 | 2012-09-01 | 2012-09-02 |  | 1 |  | X
1.4.2 |  | Due Dilligence | Understand T&C's of target vendors |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
1.4.3 |  | Due Dilligence | Review list of software licenses / contracts |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
1.5.0 |  | Due Dilligence | Application Integration Plans Defined |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
1.5.1 |  | Due Dilligence | Develop initital application blueprint |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
1.5.2 |  | Due Dilligence | Determine urgency of application deliverables due to competitive pressures |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
1.5.3 |  | Due Dilligence | Review MDM strategy |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
|  | Due Dilligence | IT Infrastructure Investment Forecast |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
|  | Due Dilligence | Identify current target plans |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
|  | Due Dilligence | Forecast typical IT investments toward integration |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
|  | Due Dilligence | Prepare 3 year investment plan |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
|  | Due Dilligence | Review 3 year investment plan |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
|  | Due Dilligence | Complete Functional Due Dilligence Report |  | Pre-Day 1 |  |  |  | 5
|  | Due Dilligence | Review materials supplied by target |  | Pre-Day 1 |  |  |  | 5
|  | Due Dilligence | Compile on-site discovery findings |  | Pre-Day 1 |  |  |  | 5
|  | Due Dilligence | Prepare IT Infrastructure report |  | Pre-Day 1 |  |  |  | 5
|  | Due Dilligence | Opportunities for revenue synergies and cost savings |  | Pre-Day 1 |  |  |  | 5
|  | Due Dilligence | Determine integration considerations |  | Pre-Day 1 |  |  |  | 5
|  | Due Dilligence | Review other functional due diligence reports |  | Pre-Day 1 |  |  |  | 5
|  | Due Dilligence | Resolve open questions/issues |  | Pre-Day 1 |  |  |  | 5
|  | Due Dilligence | Due Dilligence Management Read Out |  | Pre-Day 1 |  |  |  | 5
|  | Planning | Level 2 Site Assessment |  | Post Day 1
|  | Planning | Business Requirements Document (BRD) |  | Post Day 1
|  | Planning | Describe Core Process & key exception processes |  | Post Day 1
|  | Planning | Network assessment |  | Post Day 1
|  | Planning | Security & Risk Assessment |  | Post Day 1
|  | Planning | Identify service issues (failing or EOL solutions)
|  | Planning | Asset Inventory (physical & logical) |  | Post Day 1
|  | Planning | Create an inventory of IT M&A application assets in CMDB |  | Day 91+ | #REF! | #REF! |  | 10 | #REF! | #REF! | #REF!
|  | Planning | Facilities assessment |  | Post Day 1
|  | Planning | Document all active or paused IT projects
|  | Planning | Infrastructure Services Plans Defined |  | Day 91+ | #REF! | #REF! |  | 150 | #REF! | #REF! | #REF!
|  | Planning | Perform site visit with Infrastructure and Facilities |  | Day 30 | #REF! | #REF! |  | 15 | #REF! | #REF! | #REF!
|  | Planning | Gather overall infrastructure integration requirements, conduct capacity analysis |  | Day 30 | #REF! | #REF! |  | 15 | #REF! | #REF! | #REF!
|  | Planning | Create infrastructure BRD |  | Day 30 | #REF! | #REF! |  | 15 | #REF! | #REF! | #REF!
|  | Planning | Define and communicate estimate of IT infrastructure costs |  | Pre-Day 1 | #REF! | #REF! |  | 10 | #REF! | #REF! | #REF!
|  | Planning | If services led acquisition, determine how to align infrastructure and data center components |  | Day 60 | #REF! | #REF! |  | 30 | #REF! | #REF! | #REF!
|  | Planning | Review document storage solutions and determine migration plan. Review records retention policy. |  | Day 30 | #REF! | #REF! |  | 30 | #REF! | #REF! | #REF!
|  | Planning | Review findings with business stakeholders |  | Day 60 | #REF! | #REF! |  | 5 | #REF! | #REF! | #REF!
|  | Planning | Program Architecture Document |  | Post Day 1
|  | Planning | Architecture Scope: |  | Post Day 1
|  | Planning | Describe how architecture will enable business benefits |  | Post Day 1
|  | Planning | Describe what architecture domains are in /out of scope |  | Post Day 1
|  | Planning | Provide capability heat map |  | Post Day 1
|  | Planning | Define the scope of each transition state (for SDLC) |  | Post Day 1
|  | Planning | Solution Architecture: |  | Post Day 1
|  | Planning | Business Architecture |  | Post Day 1
|  | Planning | Operational Architecture |  | Post Day 1
|  | Planning | Information Architecture |  | Post Day 1
|  | Planning | Application Architecture |  | Post Day 1
|  | Planning | Integration Roadmap |  | Post Day 1
|  | Planning | Align Solution Architecture with UL Reference Architecture (physical & logical mapping of tools, services, and capabilities) |  | Post Day 1
|  | Planning | Draft Functional Integration plan |  | Post Day 1
|  | Planning | Incorporate Solution Architecture into Roadmap |  | Post Day 1
|  | Planning | Use a consistent set of Metrics |  | Post Day 1
|  | Planning | KPIs, Value Points, Function Points |  | Post Day 1
|  | Planning | Establish milestones to review / approve Metrics |  | Post Day 1
|  | Planning | Draft transition schedule, details & status |  | Post Day 1
|  | Planning | Publish interim SLA's and support model for the target |  | Day 30 | #REF! | #REF! |  | 30 | #REF! | #REF! | #REF!
|  | Planning | Review with Governance Teams |  | Post Day 1
2.1.0 |  | Integration | Management Office / Communication |  | Day 91+ | 2012-12-01 | 2013-01-30 |  | 60 |  |  | X
2.1.1 |  | Integration | Establish Sharepoint site for acquisition |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
2.1.2 |  | Integration | Reaffirm Day 1 IT Deliverables with Integration Exec |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
2.1.3 |  | Integration | Start the integration planning process (Day 1-30-60-90 commitments) |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
2.1.4 |  | Integration | Participate in IMO Kickoff meeting |  | Pre-Day 1 | 2012-09-01 | 2012-09-02 |  | 1 |  | X
2.1.5 |  | Integration | Plan IT Integration Kickoff meeting |  | Day 30 | 2012-10-01 | 2012-10-06 |  | 5 |  | X
2.1.6 |  | Integration | Formulate / incorporate technology communication plan |  | Day 1 | 2012-09-01 | 2012-09-11 |  | 10 |  | X
2.1.7 |  | Integration | Engage with Infrastructure team & infrastructure PM |  | Pre-Day 1 | 2012-09-01 | 2012-09-11 |  | 10 |  | X
|  | Integration | Engage with Application teams |  | Day 30 | 2012-10-01 | 2012-10-11 |  | 10 |  | X
|  | Integration | Conduct Day 1 Readiness planning sessions |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
|  | Integration | Coordinate IT activities for acquisition announcement day |  | Pre-Day 1 | 2012-09-01 | 2012-09-11 |  | 10 |  | X
|  | Integration | Confirm IT integration plan aligns with defined business strategy |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
|  | Integration | Communicate to IMO if IT plan has significant impact to other BU's IT roadmap |  | Day 30 | 2012-10-01 | 2012-10-02 |  | 1 |  | X
|  | Integration | Identify appropriate business resources to support IT integration projects |  | Day 60 | 2012-10-31 | 2012-11-10 |  | 10 |  | X
|  | Integration | Create IT overview deck for CIO staff |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
|  | Integration | Ensure target orders additional capacity for website for Day 1 |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
|  | Integration | Determine if there is an applicable IT POC for acquired products and services |  | Day 30 | 2012-10-01 | 2012-10-06 |  | 5 |  | X
|  | Integration | Determine funding for IT POC |  | Day 30 | 2012-10-01 | 2012-10-16 |  | 15 |  | X
|  | Integration | Conduct orientation for acquisition's IT leadership team |  | Day 30 | 2012-10-01 | 2012-10-02 |  | 1 |  | X
|  | Integration | Conduct IT Kickoff Meeting |  | Day 30 | 2012-10-01 | 2012-10-02 |  | 1 |  | X
|  | Integration | Establish IT integration teams |  | Day 30 | 2012-10-01 | 2012-10-16 |  | 15 |  | X
|  | Integration | Request IT teams to size work efforts |  | Day 30 | 2012-10-01 | 2012-10-16 |  | 15 |  | X
|  | Integration | Prepare GCCRB request & get CIO approval for funding |  | Day 30 | 2012-10-01 | 2012-10-06 |  | 5 |  | X
|  | Integration | Set up PMO work units |  | Day 30 | 2012-10-01 | 2012-10-06 |  | 5 |  | X
|  | Integration | Execute the POC |  | Day 30 | 2012-10-01 | 2012-11-30 |  | 60 |  | X
|  | Integration | Review integration plan with BIO |  | Day 30 | 2012-10-01 | 2012-10-06 |  | 5 |  | X
|  | Integration | Review Budget |  | Day 60 | 2012-10-31 | 2012-11-05 |  | 5 |  | X
|  | Integration | Value Creation |  | Day 91+ | 2012-12-01 | 2013-01-30 |  | 60 |  |  | X
|  | Integration | Confirm with Integration Exec the IT Integration Success Factors |  | Day 30 | 2012-10-01 | 2012-10-04 |  | 3 |  | X
|  | Integration | Prepare IT Infrastructure Synergy Model |  | Day 30 | 2012-10-01 | 2012-10-16 |  | 15 |  | X
|  | Integration | Track synergies |  | Day 60 | 2012-10-31 | 2012-12-30 |  | 60 |  |  | X
|  | Integration | Incorporate IT synergies into IT Budget |  | Day 60 | 2012-10-31 | 2012-12-30 |  | 60 |  |  | X
|  | Integration | Document financial impacts of short term solutions |  | Day 60 | 2012-10-31 | 2012-11-10 |  | 10 |  | X
|  | Integration | Review final synergy report |  | Day 91+ | 2012-12-01 | 2012-12-06 |  | 5 |  |  | X
|  | Integration | Organization & Workforce |  | Day 60 | 2012-10-31 | 2012-12-30 |  | 60 |  |  | X
|  | Integration | Identify pre-day 1 team |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
|  | Integration | Determine placement of IT employees in organization |  | Pre-Day 1 | 2012-09-01 | 2012-09-11 |  | 10 |  | X
|  | Integration | Assimilation training & orientation for new IT staff |  | Day 30 | 2012-10-01 | 2012-10-31 |  | 30 |  | X
|  | Integration | Initiate organizational optimization |  | Day 60 | 2012-10-31 | 2012-12-30 |  | 60 |  |  | X
|  | Integration | Manage culture and change readiness |  | Day 60 | 2012-10-31 | 2012-12-30 |  | 60 |  |  | X
|  | Integration | Infrastructure Services Enabled |  | Day 1 | 2012-09-01 | 2013-02-26 |  | 178 |  |  | X
|  | Integration | Security Firewalls Installed |  | Day 60 | #REF! | #REF! |  | 90 | #REF! | #REF! | #REF!
|  | Integration | Refine security & risk assessment, leverage questionnaire |  | Pre-Day 1 | #REF! | #REF! |  | 5 | #REF! | #REF! | #REF!
|  | Integration | Determine what security exceptions may be required |  | Pre-Day 1 | #REF! | #REF! |  | 5 | #REF! | #REF! | #REF!
|  | Integration | Prepare IT Infrastructure Security and Compliance Plans |  | Day 30 | #REF! | #REF! |  | 5 | #REF! | #REF! | #REF!
|  | Integration | Enable Day 1 Security and Compliance Capability |  | Day 1 | #REF! | #REF! |  | 5 | #REF! | #REF! | #REF!
|  | Integration | Review firewall and network topology |  | Day 30 | #REF! | #REF! |  | 15 | #REF! | #REF! | #REF!
|  | Integration | Assume management of/or install security gear to ensure UL has control over all ingress/egress points to UL owned networks |  | Day 30 | #REF! | #REF! |  | 15 | #REF! | #REF! | #REF!
|  | Integration | Configure firewall rules for application access |  | Day 60 | #REF! | #REF! |  | 10 | #REF! | #REF! | #REF!
|  | Integration | Conduct security review (policy & practice), leverage questionnaire |  | Day 30 | #REF! | #REF! |  | 15 | #REF! | #REF! | #REF!
|  | Integration | Special application archival requirements |  | Day 30 | #REF! | #REF! |  | 30 | #REF! | #REF! | #REF!
|  | Integration | Close security exceptions |  | Day 91+ | #REF! | #REF! |  | 90 | #REF! | #REF! | #REF!
|  | Integration | Short-term Network Connectivity Completed |  | Day 1 | 2012-09-01 | 2012-10-16 |  | 45 |  | X
|  | Integration | Perform preliminary network assessment |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
|  | Integration | Complete review of infrastructure providers |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
|  | Integration | Provide Day 1 network design |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
|  | Integration | Request Day 1 network AFE |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
|  | Integration | Order circuits & long lead time network hardware |  | Pre-Day 1 | 2012-09-01 | 2012-10-16 |  | 45 |  | X
|  | Integration | Implement Day 1 network solution |  | Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
|  | Integration | Infrastructure Federation |  | Day 90 | 1900-03-30 | 1900-04-29 |  | 30 | X
|  | Integration | Active Directory Domain Trust established |  | Day 30 | #REF! | #REF! |  | 2 | #REF! | #REF! | #REF!
|  | Integration | Define and execute Active Directory migration |  | Day 91+ | #REF! | #REF! |  | 60 | #REF! | #REF! | #REF!
|  | Integration | Employees Provisioned in Corporate Systems |  | Day 90 | #VALUE! | #VALUE! |  | 30 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | Employees provisioned in Oracle HR |  | Day 30 | 1900-01-29 | 1900-01-31 |  | 2 | X
|  | Integration | Employees provisioned in Active Directory |  | Day 30 | 1900-01-29 | 1900-01-31 |  | 2 | X
|  | Integration | Employees entered into the Global Employee Directory |  | Day 30 | 1900-01-29 | 1900-01-31 |  | 2 | X
|  | Integration | Employee mailboxes created and entered in Email Directory |  | Day 30 | 1900-01-29 | 1900-01-31 |  | 2 | X
|  | Integration | Initial Collaberation Solutions Established |  | Day 90 | 2012-11-30 | 2012-12-30 |  | 30 |  |  | X
|  | Integration | Enable Lync messaging between acquisition and corporate |  | Pre-Day 1 | 0 | 1900-01-04 |  | 5 | X
|  | Integration | Microsoft Lync deployed to all employees |  | Day 30 | 1900-01-29 | 1900-01-31 |  | 2 | X
|  | Integration | Sharepoint access established for key staff |  | Day 30 | 1900-01-29 | 1900-01-31 |  | 2 | X
|  | Integration | KMS access established for key staff |  | Day 30 | 1900-01-29 | 1900-01-31 |  | 2 | X
|  | Integration | Employee informational and Welfare Solutions Enabled |  | Day 90 | 1900-03-30 | 1900-04-29 |  | 30 | X
|  | Integration | Intranet access established |  | Day 30 | 2012-10-01 | 2012-10-03 |  | 2 |  | X
|  | Integration | CEO webcast access confirmed |  | Day 30 | #VALUE! | #VALUE! |  | 2 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | Employee HR orientation conducted |  | Day 30 | #VALUE! | #VALUE! |  | 2 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | DNS provisioned for UL.COM domain |  | Day 30 | 1900-01-29 | 1900-01-31 |  | 2 | X
|  | Integration | End State Network Connectivity Completed |  | Day 90 | 2012-11-30 | 2012-12-30 |  | 30 |  |  | X
|  | Integration | Conduct Network integration Site Survey |  | Day 30 | 2012-10-01 | 2012-10-03 |  | 2 |  | X
|  | Integration | Plan & Design full network integration solution |  | Day 60 | 2012-10-31 | 2012-11-10 |  | 10 |  | X
|  | Integration | Request AFE for remaining network equipment |  | Day 60 | 2012-10-31 | 2012-11-05 |  | 5 |  | X
|  | Integration | Order network equipment |  | Day 60 | 2012-10-31 | 2012-11-30 |  | 30 |  | X
|  | Integration | Escalate long lead times with vendor |  | Day 30 | 2012-10-01 | 2012-10-06 |  | 5 |  | X
|  | Integration | Configure and test network equipment |  | Day 90 | 2012-11-30 | 2012-12-10 |  | 10 |  |  | X
|  | Integration | Transition 3rd party DNS |  | Day 90 | 2012-11-30 | 2012-12-05 |  | 5 |  |  | X
|  | Integration | Design and migrate Extranet |  | Day 90 | 2012-11-30 | 2012-12-10 |  | 10 |  |  | X
|  | Integration | Remote connectivity established |  | Day 1 | 2012-09-01 | 2012-09-04 |  | 3 |  | X
|  | Integration | Document requirements |  | Pre-Day 1 | 2012-09-01 | 2012-09-03 |  | 2 |  | X
|  | Integration | Review requirements with Remote Application Delivery Services |  | Pre-Day 1 | 2012-09-01 | 2012-09-04 |  | 3 |  | X
|  | Integration | Define solution and tailor user guide accordingly |  | Pre-Day 1 | 2012-09-01 | 2012-09-03 |  | 2 |  | X
|  | Integration | Service Desk Completed |  | Day 30 | #VALUE! | #VALUE! |  | 10 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | Complete Service Desk plan |  | Day 60 | #REF! | #REF! |  | 30 | #REF! | #REF! | #REF!
|  | Integration | Mobile Messaging Completed |  | Day 30 | 2012-10-01 | 2012-10-11 |  | 10 |  | X
|  | Integration | Communicate mobile messaging policies and approval process to target and business sponsor |  | Day 30 | 2012-10-01 | 2012-10-02 |  | 1 |  | X
|  | Integration | Request a list of current mobile devices, types and contracts |  | Day 30 | 2012-10-01 | 2012-10-11 |  | 10 |  | X
|  | Integration | Get approved list of employees who will receive a UL issued device |  | Day 30 | 2012-10-01 | 2012-10-11 |  | 10 |  | X
|  | Integration | Order mobile messaging devices for team members |  | Day 30 | 2012-10-01 | 2012-10-11 |  | 10 |  | X
|  | Integration | Email Migration Completed |  | Day 1 | 2012-09-01 | 2012-10-01 |  | 30 |  | X
|  | Integration | Validate email server capacity is available to support new acquisition |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
|  | Integration | create email accounts (automated process after HR load) |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
|  | Integration | Set up email forwarding to target |  | Pre-Day 1 | 2012-09-01 | 2012-09-04 |  | 3 |  | X
|  | Integration | Reverse email forwarding as soon as BB are received |  | Day 91+ | 2012-12-01 | 2012-12-06 |  | 5 |  |  | X
|  | Integration | Migrate email from legacy mail to UL O365 |  | Day 91+ | 2012-12-01 | 2012-12-31 |  | 30 |  |  | X
|  | Integration | Plan for decommisioning of target email servers |  | Day 91+ | 2012-12-01 | 2012-12-16 |  | 15 |  |  | X
|  | Integration | Decommision target email environment |  | Day 91+ | 2012-12-01 | 2012-12-16 |  | 15 |  |  | X
|  | Integration | Virtual Workplace Implementation Completed |  | Day 91+ | 1900-03-31 | 1900-04-30 |  | 30 | X
|  | Integration | Cable Plant Upgraded |  | Day 91+ | 1900-03-31 | 1900-04-30 |  | 30 | X
|  | Integration | LAN and Wireless Networking Solutions Implemented |  | Day 91+ | #VALUE! | #VALUE! |  | 30 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | Voice and Contact Center Solution Implemented |  | Day 91+ | 2012-12-01 | 2012-12-31 |  | 30 |  |  | X
|  | Integration | Identify and assess target voice infrastructure |  | Day 30 | 2012-10-01 | 2012-10-06 |  | 5 |  | X
|  | Integration | Update phone numbers in corporate directory |  | Day 30 | 2012-10-01 | 2012-10-31 |  | 30 |  | X
|  | Integration | Document voice and contact center requirements and business process flows. Consider country specific codes and regulations. |  | Day 30 | 2012-10-01 | 2012-10-21 |  | 20 |  | X
|  | Integration | Design voice and contact center solution |  | Day 60 | 2012-10-31 | 2012-11-10 |  | 10 |  | X
|  | Integration | Provide recommendation on voice and contact center solution to business stakeholders |  | Day 60 | 2012-10-31 | 2012-11-05 |  | 5 |  | X
|  | Integration | Request resources based on voice and contact center solution (i.e. ACD, Telecom, Backbone, etc.) |  | Day 60 | 2012-10-31 | 2012-11-03 |  | 3 |  | X
|  | Integration | Order hardware/software/carrier services for voice and contact center solution |  | Day 60 | 2012-10-31 | 2012-11-01 |  | 1 |  | X
|  | Integration | Add IDD functionality and agent skills to ACD |  | Day 90 | 2012-11-30 | 2012-12-10 |  | 10 |  |  | X
|  | Integration | Deploy and test voice and contact center solution |  | Day 91+ | 2012-12-01 | 2012-12-06 |  | 5 |  |  | X
|  | Integration | Capture telecom's billing information to be loaded into the telecom system |  | Day 60 | 2012-10-31 | 2012-11-10 |  | 10 |  | X
|  | Integration | Data Center and Lab Integration Plan Defined |  | Day 30 | 2012-10-01 | 2012-10-31 |  | 30 |  | X
|  | Integration | Perform assessment of data center and labs |  | Pre-Day 1 | 2012-09-01 | 2012-09-06 |  | 5 |  | X
|  | Integration | Determine data center consolidations |  | Day 30 | 2012-10-01 | 2012-10-31 |  | 30 |  | X
|  | Integration | Infrastructure monitoring |  | Day 30 | 2012-10-01 | 2012-10-31 |  | 30 |  | X
|  | Integration | Server and Storage Integration Plan Defined |  | Day 90 | 2012-11-30 | 2013-01-29 |  | 60 |  |  | X
|  | Integration | Obtain inventory of servers and storage |  | Day 30 | 2012-10-01 | 2012-10-06 |  | 5 |  | X
|  | Integration | Indentify plan for server refresh and/or relocation |  | Day 30 | 2012-10-01 | 2012-10-11 |  | 10 |  | X
|  | Integration | Define server refresh strategy |  | Day 30 | 2012-10-01 | 2012-10-11 |  | 10 |  | X
|  | Integration | Review server refresh findings with business stakeholders |  | Day 60 | 2012-10-31 | 2012-11-05 |  | 5 |  | X
|  | Integration | Execute server refresh strategy |  | Day 90 | 2012-11-30 | 2013-01-29 |  | 60 |  |  | X
|  | Integration | Determine if legacy servers are running on EOL software and the ability to migrate to UL standards |  | Day 90 | 2012-11-30 | 2013-01-29 |  | 60 |  |  | X
|  | Integration | Laptops Distributed |  | Day 1 |  | #VALUE! |  | 60 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | Identify PC requirements for Day 1 clients |  | Pre-Day 1 |  | #VALUE! |  | 5 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | Review proposal needs |  | Pre-Day 1 |  | #VALUE! |  | 5 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | Create client computing AFE by region |  | Pre-Day 1 |  | #VALUE! |  | 5 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | Order client pc's for every employee at target company |  | Pre-Day 1 |  | #VALUE! |  | 5 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | Work with HR to ensure appropriate lead time for employee load to Oracle HR |  | Pre-Day 1 |  | #VALUE! |  | 5 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | Contact vendor to expedite client orders |  | Pre-Day 1 |  | #VALUE! |  | 5 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | Build delivery and deployment timeline |  | Pre-Day 1 |  | #VALUE! |  | 3 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | Create AD accounts and email |  | Pre-Day 1 |  | #VALUE! |  | 5 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | Request Citrix accounts for all employees |  | Pre-Day 1 |  | #VALUE! |  | 5 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | Prepare notebooks for deployment, Identify POC for delivery, obtain staging area at target |  | Pre-Day 1 |  | #VALUE! |  | 10 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | Order laptop locks using p-card |  | Pre-Day 1 |  | #VALUE! |  | 10 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | Tailor user guide for target |  | Pre-Day 1 |  | #VALUE! |  | 5 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | Deliver workstations and laptop locks to target |  | Pre-Day 1 |  | #VALUE! |  | 5 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | Determine if site(s) require full-time onsite support personnel |  | Pre-Day 1 |  | #VALUE! |  | 5 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | Deploy clients to acquired complany on Day 1 |  | Pre-Day 1 |  | #VALUE! |  | 3 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | Provide onsite support for two weeks |  | Day 1 |  | #VALUE! |  | 10 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | Distribute User Guide and IT Corporate Policy / Guidelines |  | Day 30 | #VALUE! | #VALUE! |  | 1 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | Develop Client migration plan |  | Day 1 |  | #VALUE! |  | 15 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | Communicate and execute the asset recovery process |  | Day 30 | #VALUE! | #VALUE! |  | 45 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | Migrate client data |  | Day 91+ | #VALUE! | #VALUE! |  | 30 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | Migrate acquired company to managed printer solution |  | Day 91+ | #VALUE! | #VALUE! |  | 30 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | Turn over support to internal service desk |  | Day 91+ | #VALUE! | #VALUE! |  | 60 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | Disaster Recovery Plans Defined |  | Day 91+ | #REF! | #REF! |  | 150 | #REF! | #REF! | #REF!
|  | Integration | Evaluate and implement DR solution |  | Day 91+ | #REF! | #REF! |  | 90 | #REF! | #REF! | #REF!
|  | Integration | Perform assessment of DR capabilities |  | Pre-Day 1 | #REF! | #REF! |  | 5 | #REF! | #REF! | #REF!
|  | Integration | Perform assessment of DR strategy and implementation |  | Day 60 | #REF! | #REF! |  | 10 | #REF! | #REF! | #REF!
|  | Integration | Implement improvements to DR plan |  | Day 91+ | #REF! | #REF! |  | 60 | #REF! | #REF! | #REF!
|  | Integration | Execution Planning Services Enabled |  | Day 1 | 2012-09-01 | 2013-02-26 |  | 178 |  |  | X
Change Management and Budgeting Processes implemented
(PMO, SDLC, QA, IT Finance, Governance, Service Mgmt, EA)
Asset Management implemented
Facilities, Computing Equipment, Office Equipment, Lab Inventory, Lab Raw Materials, and Software/Logical Assets
|  | Integration | Engage the UL retired capital team to onboard the acquisition on apprpriate disposal process |  | Day 30 | #REF! | #REF! |  | 5 | #REF! | #REF! | #REF!
|  | Integration | Software, Vendor Management and Procurement Implemented |  | Day 91+ | 2012-12-01 | 2013-03-01 |  | 90 |  |  | X
|  | Integration | Confirm IT assumptions for software contracts and licenses |  | Day 30 | 2012-10-01 | 2012-10-06 |  | 5 |  | X
|  | Integration | Partner with Procurement to understand impact of UL licensing agreements on target |  | Day 30 | 2012-10-01 | 2012-10-06 |  | 5 |  | X
|  | Integration | Rationalize Vendor & Software license contracts |  | Day 30 | 2012-10-01 | 2012-10-31 |  | 30 |  | X
|  | Integration | Submit list of 3rd party software licenses to standards board for review |  | Day 90 | 2012-11-30 | 2012-12-10 |  | 10 |  |  | X
|  | Integration | Attend standards review board |  | Day 90 | 2012-11-30 | 2012-12-05 |  | 5 |  |  | X
|  | Integration | Ensure 3rd party software is added to CMDB and support model is in place |  | Day 91+ | 2012-12-01 | 2012-12-11 |  | 10 |  |  | X
|  | Integration | Participate with Procurement for security risk assessments of non-standard vendors |  | Day 90 | 2012-11-30 | 2013-02-28 |  | 90 |  |  | X
|  | Integration | Operational Services Enabled |  | Day 1 | 2012-09-01 | 2013-02-26 |  | 178 |  |  | X
|  | Integration | Application Integration Plans Defined |  | Day 91+ | 2012-12-01 | 2013-03-31 |  | 120 |  |  | X
|  | Integration | Develop application migration strategy |  | Pre-Day 1 | 2012-09-01 | 2012-09-11 |  | 10 |  | X
|  | Integration | Ensure preservation of target IP value |  | Pre-Day 1 | 2012-09-01 | 2012-09-02 |  | 1 |  | X
|  | Integration | Establish Day 1 applications |  | Pre-Day 1 | 2012-09-01 | 2012-09-11 |  | 10 |  | X
|  | Integration | Plan Day 1 access to appropriate applications |  | Pre-Day 1 | 2012-09-01 | 2012-09-11 |  | 10 |  | X
|  | Integration | Alert relevant application teams of upcoming integration effort |  | Pre-Day 1 | 2012-09-01 | 2012-09-02 |  | 1 |  | X
|  | Integration | Enable Day 1 applications |  | Day 1 | 2012-09-01 | 2012-09-16 |  | 15 |  | X
|  | Integration | Migrate acquired company strategic apps to UL data center |  | Day 91+ | 2012-12-01 | 2013-01-30 |  | 60 |  |  | X
|  | Integration | Create PAD document |  | Day 60 | 2012-10-31 | 2012-11-21 |  | 21 |  | X
|  | Integration | Develop application integration roadmap |  | Day 60 | 2012-10-31 | 2012-12-30 |  | 60 |  |  | X
|  | Integration | Evaluate & formulate MDM migration strategy for Customer Asset and Product detail |  | Day 30 | 2012-10-01 | 2012-10-11 |  | 10 |  | X
|  | Integration | Integrate with UL's MDM hub |  | Day 60 | 2012-10-31 | 2012-12-30 |  | 60 |  |  | X
|  | Integration | Incorporate MDM strategy for customer asset and product |  | Day 90 | 2012-11-30 | 2013-01-29 |  | 60 |  |  | X
|  | Integration | Sales Optimization |  | Day 30
|  | Integration | Draft & Manage Program Plan & Master Schedule covering sales operations |  | Day 30
|  | Integration | Track delivery timelines and coordinate with Data Management |  | Day 30
|  | Integration | Weekly CRM meetings with Acquisition Sales Leads, IT RMs, & UL Sales Ops Leads |  | Day 30
|  | Integration | M&A IT responsible for drafting BRD & Solution Architecture for Sales Integration |  | Day 30
|  | Integration | Acquisition Account Mapping |  | Day 30
|  | Integration | Data Profiling |  | Day 30
|  | Integration | Data Matching, Mapping, & Transformation |  | Day 30
|  | Integration | Data Cleansing |  | Day 30
|  | Integration | Alignment with Data Governance (customer & marketing data) |  | Day 30
|  | Integration | Identify account delivery points (pipeline & customer info) |  | Day 30
|  | Integration | Educate UL Sales Ops on acquisition's sales pipeline |  | Day 30
|  | Integration | Train acquisition staff on UL tool(s) |  | Day 30
|  | Integration | Provide buddy system (pairing UL CRM SME with acquisition sales manager) to ensure solution meets their needs (process, reports, metrics, data alignment) |  | Day 30
|  | Integration | CRM Migration Completed |  | Day 60 | 2012-10-31 | 2012-11-20 |  | 20 |  | X
|  | Integration | Gather CRM integration requirements |  | Day 30 | 2012-10-01 | 2012-10-11 |  | 10 |  | X
|  | Integration | Design CRM system changes |  | Day 60 | 2012-10-31 | 2012-11-20 |  | 20 |  | X
|  | Integration | Code CRM system changes |  | Day 60 | 2012-10-31 | 2012-11-20 |  | 20 |  | X
|  | Integration | knowledge transfer |  | Day 60 | 2012-10-31 | 2012-11-05 |  | 5 |  | X
|  | Integration | System integration test |  | Day 60 | 2012-10-31 | 2012-11-20 |  | 20 |  | X
|  | Integration | Prototype review with business |  | Day 60 | 2012-10-31 | 2012-11-05 |  | 5 |  | X
|  | Integration | Business accounting matching completed |  | Day 90 | 2012-11-30 | 2012-12-01 |  | 1 |  |  | X
|  | Integration | User acceptance test |  | Day 90 | 2012-11-30 | 2012-12-10 |  | 10 |  |  | X
|  | Integration | CRM system go live |  | Day 90 | 2012-11-30 | 2012-12-01 |  | 1 |  |  | X
|  | Integration | Buy & Pay Completed |  | Day 60 | 1900-02-28 | 1900-03-20 |  | 20 | X
|  | Integration | Design future state application platform |  | Day 60 | 1900-02-28 | 1900-04-29 |  | 60 | X
|  | Integration | Develop target system knowledge transfer |  | Day 60 | 1900-02-28 | 1900-03-30 |  | 30 | X
|  | Integration | Change applications - deploy code |  | Day 91+ | 1900-03-31 | 1900-07-29 |  | 120 | X
|  | Integration | System integration test |  | Day 91+ | 1900-03-31 | 1900-04-30 |  | 30 | X
|  | Integration | User acceptance test |  | Day 91+ | 1900-03-31 | 1900-04-15 |  | 15 | X
|  | Integration | System go live |  | Day 91+ | 1900-03-31 | 1900-04-05 |  | 5 | X
|  | Integration | Decommision and dispose of retired infrastructure associated with retired apps |  | Day 91+ | 1900-03-31 | 1900-05-30 |  | 60 | X
|  | Integration | Aria Completed |  | Day 60 | 1900-02-28 | 1900-03-20 |  | 20 | X
|  | Integration | Design future state application platform |  | Day 60 | 1900-02-28 | 1900-04-29 |  | 60 | X
|  | Integration | Develop target system knowledge transfer |  | Day 60 | 1900-02-28 | 1900-03-30 |  | 30 | X
|  | Integration | Change applications - deploy code |  | Day 91+ | 1900-03-31 | 1900-07-29 |  | 120 | X
|  | Integration | System integration test |  | Day 91+ | 1900-03-31 | 1900-04-30 |  | 30 | X
|  | Integration | User acceptance test |  | Day 91+ | 1900-03-31 | 1900-04-15 |  | 15 | X
|  | Integration | System go live |  | Day 91+ | 1900-03-31 | 1900-04-05 |  | 5 | X
|  | Integration | Decommision and dispose of retired infrastructure associated with retired apps |  | Day 91+ | 1900-03-31 | 1900-05-30 |  | 60 | X
|  | Integration | LMS Completed |  | Day 60 | 1900-02-28 | 1900-03-20 |  | 20 | X
|  | Integration | Design future state application platform |  | Day 60 | 1900-02-28 | 1900-04-29 |  | 60 | X
|  | Integration | Develop target system knowledge transfer |  | Day 60 | 1900-02-28 | 1900-03-30 |  | 30 | X
|  | Integration | Change applications - deploy code |  | Day 91+ | 1900-03-31 | 1900-07-29 |  | 120 | X
|  | Integration | System integration test |  | Day 91+ | 1900-03-31 | 1900-04-30 |  | 30 | X
|  | Integration | User acceptance test |  | Day 91+ | 1900-03-31 | 1900-04-15 |  | 15 | X
|  | Integration | System go live |  | Day 91+ | 1900-03-31 | 1900-04-05 |  | 5 | X
|  | Integration | Decommision and dispose of retired infrastructure associated with retired apps |  | Day 91+ | 1900-03-31 | 1900-05-30 |  | 60 | X
|  | Integration | Differentiating Services Enabled |  | Day 1 |  | #VALUE! |  | 178 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | LIMS Completed |  | Day 60 | 1900-02-28 | 1900-03-20 |  | 20 | X
|  | Integration | Design future state application platform |  | Day 60 | 1900-02-28 | 1900-04-29 |  | 60 | X
|  | Integration | Develop target system knowledge transfer |  | Day 60 | 1900-02-28 | 1900-03-30 |  | 30 | X
|  | Integration | Change applications - deploy code |  | Day 91+ | 1900-03-31 | 1900-07-29 |  | 120 | X
|  | Integration | System integration test |  | Day 91+ | 1900-03-31 | 1900-04-30 |  | 30 | X
|  | Integration | User acceptance test |  | Day 91+ | 1900-03-31 | 1900-04-15 |  | 15 | X
|  | Integration | System go live |  | Day 91+ | 1900-03-31 | 1900-04-05 |  | 5 | X
|  | Integration | Decommision and dispose of retired infrastructure associated with retired apps |  | Day 91+ | 1900-03-31 | 1900-05-30 |  | 60 | X
|  | Integration | Portal Services Completed |  | Day 60 | 1900-02-28 | 1900-03-20 |  | 20 | X
|  | Integration | Design future state application platform |  | Day 60 | #VALUE! | #VALUE! |  | 60 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | Develop target system knowledge transfer |  | Day 60 | #VALUE! | #VALUE! |  | 30 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | Change applications - deploy code |  | Day 91+ | #VALUE! | #VALUE! |  | 120 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | System integration test |  | Day 91+ | #VALUE! | #VALUE! |  | 30 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | User acceptance test |  | Day 91+ | #VALUE! | #VALUE! |  | 15 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | System go live |  | Day 91+ | #VALUE! | #VALUE! |  | 5 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | Decommision and dispose of retired infrastructure associated with retired apps |  | Day 91+ | #VALUE! | #VALUE! |  | 60 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | Business Transition Complete |  | Day 1 | 0 | 1900-06-26 |  | 178 | X
|  | Post-Integration | Measure, Assess, and Transition |  | Day 91+
|  | Integration | Confirm decommision Plan for EOL products |  | Day 91+ | #REF! | #REF! |  | 60 | #REF! | #REF! | #REF!
|  | Post-Integration | Complete IT End of integration support matrix |  | Day 91+ | #REF! | #REF! |  | 10 | #REF! | #REF! | #REF!
|  | Post-Integration | key functional integration milestones completed |  | Day 91+
|  | Post-Integration | Major Issues & Risks have been addressed |  | Day 91+
|  | Post-Integration | Minor Issues & Risks have been addressed or signed off (but tracked) |  | Day 91+
|  | Post-Integration | synergies realized |  | Day 91+
|  | Post-Integration | value points preserved |  | Day 91+
|  | Post-Integration | Business Plan optimized |  | Day 91+
|  | Post-Integration | IT Architecture Roadmap Updated |  | Day 91+
|  | Post-Integration | Transfer ownership to operational teams & service owners |  | Day 91+
|  | Integration | Closeout presentation to IMO, BIO & Stakeholders |  | Day 91+ | #VALUE! | #VALUE! |  | 15 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | Recognize the team |  | Day 91+ | #VALUE! | #VALUE! |  | 1 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | Prepare knowledge transfer documents |  | Day 91+ | #VALUE! | #VALUE! |  | 10 | #VALUE! | #VALUE! | #VALUE!
|  | Integration | Conduct lessons learned session with team |  | Day 91+ | #VALUE! | #VALUE! |  | 5 | #VALUE! | #VALUE! | #VALUE!
Formulas:
R = [Phase This Task Will Be Completed]+90
Estimated End Date = [Status Key:]+[On track]
Note on J6: These fields will automatically populate based on start date and estimated end date.
Note on K6: These fields will automatically populate based on start date, estimated end date, and the projected phase end dates provided below.

## Sheet1
Task Focus | Task Description | Non- | Timing
Neg
(Y/N)
Due Dilligence | Management Office / Communication |  | Pre-Day 1
Due Dilligence | Determine if TSA is required and application impacts as a result |  | Pre-Day 1
Due Dilligence | Create M&A Council DD and Integration Planning Report |  | Pre-Day 1
Due Dilligence | Evaluate International Constraints for Day 1 Deliverables |  | Pre-Day 1
Due Dilligence | Create CIO Staff IT Due Dilligence Email and Report |  | Pre-Day 1
Due Dilligence | Evaluate legacy acquisition network for sustaining and scaling |  | Pre-Day 1
Due Dilligence | IT integration cost budget defined and approved |  | Pre-Day 1
Due Dilligence | Value Creation |  | Pre-Day 1
Due Dilligence | Analyze IT Financials of target |  | Pre-Day 1
Due Dilligence | Identify high level synergy opportunities |  | Pre-Day 1
Due Dilligence | Understand common baseline technologies for target industry |  | Pre-Day 1
Due Dilligence | Organization & Workforce |  | Pre-Day 1
Due Dilligence | Assess IT Organization |  | Pre-Day 1
Due Dilligence | Evaluate cultural considerations |  | Pre-Day 1
Due Dilligence | Create IT retention list |  | Pre-Day 1
Due Dilligence | Software & Vendor Management |  | Pre-Day 1
Due Dilligence | Review software licensing management & renewal process |  | Pre-Day 1
Due Dilligence | Understand T&C's of target vendors |  | Pre-Day 1
Due Dilligence | Review list of software licenses / contracts |  | Pre-Day 1
Due Dilligence | Application Integration Plans Defined |  | Pre-Day 1
Due Dilligence | Develop initital application blueprint |  | Pre-Day 1
Due Dilligence | Determine urgency of application deliverables due to competitive pressures |  | Pre-Day 1
Due Dilligence | Review MDM strategy |  | Pre-Day 1
Integration | Management Office / Communication |  | Day 91+
Integration | Establish Sharepoint site for acquisition |  | Pre-Day 1
Integration | Reaffirm Day 1 IT Deliverables with Integration Exec |  | Pre-Day 1
Integration | Start the integration planning process (Day 1-30-60-90 commitments) |  | Pre-Day 1
Integration | Participate in IMO Kickoff meeting |  | Pre-Day 1
Integration | Plan IT Integration Kickoff meeting |  | Day 30
Integration | Formulate / incorporate technology communication plan |  | Day 1
Integration | Engage with Infrastructure team & infrastructure PM |  | Pre-Day 1
Integration | Engage with Application teams |  | Day 30
Integration | Conduct Day 1 Readiness planning sessions |  | Pre-Day 1
Integration | Coordinate IT activities for acquisition announcement day |  | Pre-Day 1
Integration | Confirm IT integration plan aligns with defined business strategy |  | Pre-Day 1
Integration | Communicate to IMO if IT plan has significant impact to other BU's IT roadmap |  | Day 30
Integration | Identify appropriate business resources to support IT integration projects |  | Day 60
Integration | Create IT overview deck for CIO staff |  | Pre-Day 1
Integration | Ensure target orders additional capacity for website for Day 1 |  | Pre-Day 1
Integration | Determine if there is an applicable IT POC for acquired products and services |  | Day 30
Integration | Determine funding for IT POC |  | Day 30
Integration | Conduct orientation for acquisition's IT leadership team |  | Day 30
Integration | Conduct IT Kickoff Meeting |  | Day 30
Integration | Establish IT integration teams |  | Day 30
Integration | Request IT teams to size work efforts |  | Day 30
Integration | Prepare GCCRB request & get CIO approval for funding |  | Day 30
Integration | Set up PMO work units |  | Day 30
Integration | Execute the POC |  | Day 30
Integration | Review integration plan with BIO |  | Day 30
Integration | Review Budget |  | Day 60
Integration | Closeout presentation to IMO, BIO & Stakeholders |  | Day 91+
Integration | Recognize the team |  | Day 91+
Integration | Prepare knowledge transfer documents |  | Day 91+
Integration | Conduct lessons learned session with team |  | Day 91+
Integration | Value Creation |  | Day 91+
Integration | Confirm with Integration Exec the IT Integration Success Factors |  | Day 30
Integration | Prepare IT Infrastructure Synergy Model |  | Day 30
Integration | Track synergies |  | Day 60
Integration | Incorporate IT synergies into IT Budget |  | Day 60
Integration | Document financial impacts of short term solutions |  | Day 60
Integration | Review final synergy report |  | Day 91+
Integration | Organization & Workforce |  | Day 60
Integration | Identify pre-day 1 team |  | Pre-Day 1
Integration | Determine placement of IT employees in organization |  | Pre-Day 1
Integration | Assimilation training & orientation for new IT staff |  | Day 30
Integration | Initiate organizational optimization |  | Day 60
Integration | Manage culture and change readiness |  | Day 60
Integration | Software & Vendor Management |  | Day 91+
Integration | Confirm IT assumptions for software contracts and licenses |  | Day 30
Integration | Partner with Procurement to understand impact of UL licensing agreements on target |  | Day 30
Integration | Rationalize Vendor & Software license contracts |  | Day 30
Integration | Submit list of 3rd party software licenses to standards board for review |  | Day 90
Integration | Attend standards review board |  | Day 90
Integration | Ensure 3rd party software is added to CMDB and support model is in place |  | Day 91+
Integration | Participate with Procurement for security risk assessments of non-standard vendors |  | Day 90
Integration | Day 1 Network Connectivity Completed |  | Day 1
Integration | Perform preliminary network assessment |  | Pre-Day 1
Integration | Complete review of infrastructure providers |  | Pre-Day 1
Integration | Provide Day 1 network design |  | Pre-Day 1
Integration | Request Day 1 network AFE |  | Pre-Day 1
Integration | Order circuits & long lead time network hardware |  | Pre-Day 1
Integration | Implement Day 1 network solution |  | Day 1
Integration | Enable Lync messaging between acquisition and corporate |  | Pre-Day 1
Integration | End State Netwrok Connectivity Completed |  | Day 90
Integration | Conduct Network integration Site Survey |  | Day 30
Integration | Plan & Design full network integration solution |  | Day 60
Integration | Request AFE for remaining network equipment |  | Day 60
Integration | Order network equipment |  | Day 60
Integration | Escalate long lead times with vendor |  | Day 30
Integration | Configure and test network equipment |  | Day 90
Integration | Transition 3rd party DNS |  | Day 90
Integration | Design and migrate Extranet |  | Day 90
Integration | Remote connectivity established |  | Day 1
Integration | Document requirements |  | Pre-Day 1
Integration | Review requirements with Remote Application Delivery Services |  | Pre-Day 1
Integration | Define solution and tailor user guide accordingly |  | Pre-Day 1
Integration | Laptops Distributed |  | Day 1
Integration | Identify PC requirements for Day 1 clients |  | Pre-Day 1
Integration | Review proposal needs |  | Pre-Day 1
Integration | Create client computing AFE by region |  | Pre-Day 1
Integration | Order client pc's for every employee at target company |  | Pre-Day 1
Integration | Work with HR to ensure appropriate lead time for employee load to Oracle HR |  | Pre-Day 1
Integration | Contact vendor to expedite client orders |  | Pre-Day 1
Integration | Build delivery and deployment timeline |  | Pre-Day 1
Integration | Create AD accounts and email |  | Pre-Day 1
Integration | Request Citrix accounts for all employees |  | Pre-Day 1
Integration | Prepare notebooks for deployment, Identify POC for delivery, obtain staging area at target |  | Pre-Day 1
Integration | Order laptop locks using p-card |  | Pre-Day 1
Integration | Tailor user guide for target |  | Pre-Day 1
Integration | Deliver workstations and laptop locks to target |  | Pre-Day 1
Integration | Determine if site(s) require full-time onsite support personnel |  | Pre-Day 1
Integration | Deploy clients to acquired complany on Day 1 |  | Pre-Day 1
Integration | Provide onsite support for two weeks |  | Day 1
Integration | Distribute User Guide and IT Corporate Policy / Guidelines |  | Day 30
Integration | Develop Client migration plan |  | Day 1
Integration | Communicate and execute the asset recovery process |  | Day 30
Integration | Migrate client data |  | Day 91+
Integration | Migrate acquired company to managed printer solution |  | Day 91+
Integration | Turn over support to internal service desk |  | Day 91+
Integration | Mobile Messaging Completed |  | Day 30
Integration | Communicate mobile messaging policies and approval process to target and business sponsor |  | Day 30
Integration | Request a list of current mobile devices, types and contracts |  | Day 30
Integration | Get approved list of employees who will receive a UL issued device |  | Day 30
Integration | Order mobile messaging devices for team members |  | Day 30
Integration | Email Configured |  | Day 1
Integration | Validate email server capacity is available to support new acquisition |  | Pre-Day 1
Integration | create email accounts (automated process after HR load) |  | Pre-Day 1
Integration | Set up email forwarding to target |  | Pre-Day 1
Integration | Reverse email forwarding as soon as BB are received |  | Day 91+
Integration | Migrate email from legacy mail to UL O365 |  | Day 91+
Integration | Plan for decommisioning of target email servers |  | Day 91+
Integration | Decommision target email environment |  | Day 91+
Integration | Voice and Contact Center Solution Implemented |  | Day 91+
Integration | Identify and assess target voice infrastructure |  | Day 30
Integration | Update phone numbers in corporate directory |  | Day 30
Integration | Document voice and contact center requirements and business process flows. Consider country specific codes and regulations. |  | Day 30
Integration | Design voice and contact center solution |  | Day 60
Integration | Provide recommendation on voice and contact center solution to business stakeholders |  | Day 60
Integration | Request resources based on voice and contact center solution (i.e. ACD, Telecom, Backbone, etc.) |  | Day 60
Integration | Order hardware/software/carrier services for voice and contact center solution |  | Day 60
Integration | Add IDD functionality and agent skills to ACD |  | Day 90
Integration | Deploy and test voice and contact center solution |  | Day 91+
Integration | Capture telecom's billing information to be loaded into the telecom system |  | Day 60
Integration | Data Center and Lab Integration Plan Defined |  | Day 30
Integration | Perform assessment of data center and labs |  | Pre-Day 1
Integration | Determine data center consolidations |  | Day 30
Integration | Infrastructure monitoring |  | Day 30
Integration | Server and Storage Integration Plan Defined |  | Day 90
Integration | Obtain inventory of servers and storage |  | Day 30
Integration | Indentify plan for server refresh and/or relocation |  | Day 30
Integration | Define server refresh strategy |  | Day 30
Integration | Review server refresh findings with business stakeholders |  | Day 60
Integration | Execute server refresh strategy |  | Day 90
Integration | Determine if legacy servers are running on EOL software and the ability to migrate to UL standards |  | Day 90
Integration | Security Firewalls Installed |  | Day 60
Integration | Refine security & risk assessment, leverage questionnaire |  | Pre-Day 1
Integration | Determine what security exceptions may be required |  | Pre-Day 1
Integration | Prepare IT Infrastructure Security and Compliance Plans |  | Day 30
Integration | Enable Day 1 Security and Compliance Capability |  | Day 1
Integration | Review firewall and network topology |  | Day 30
Integration | Assume management of/or install security gear to ensure UL has control over all ingress/egress points to UL owned networks |  | Day 30
Integration | Configure firewall rules for application access |  | Day 60
Integration | Conduct security review (policy & practice), leverage questionnaire |  | Day 30
Integration | Special application archival requirements |  | Day 30
Integration | Close security exceptions |  | Day 91+
Integration | Application Integration Plans Defined |  | Day 91+
Integration | Develop application migration strategy |  | Pre-Day 1
Integration | Ensure preservation of target IP value |  | Pre-Day 1
Integration | Establish Day 1 applications |  | Pre-Day 1
Integration | Plan Day 1 access to appropriate applications |  | Pre-Day 1
Integration | Alert relevant application teams of upcoming integration effort |  | Pre-Day 1
Integration | Enable Day 1 applications |  | Day 1
Integration | Migrate acquired company strategic apps to UL data center |  | Day 91+
Integration | Create PAD document |  | Day 60
Integration | Develop application integration roadmap |  | Day 60
Integration | Design future state application platform |  | Day 60
Integration | Develop target system knowledge transfer |  | Day 60
Integration | Change applications - deploy code |  | Day 91+
Integration | System integration test |  | Day 91+
Integration | User acceptance test |  | Day 91+
Integration | System go live |  | Day 91+
Integration | Decommision and dispose of retired infrastructure associated with retired apps |  | Day 91+
Integration | Evaluate & formulate MDM migration strategy for Customer Asset and Product detail |  | Day 30
Integration | Integrate with UL's MDM hub |  | Day 60
Integration | Incorporate MDM strategy for customer asset and product |  | Day 90
Integration | CRM Migration Completed |  | Day 60
Integration | Gather CRM integration requirements |  | Day 30
Integration | Design CRM system changes |  | Day 60
Integration | Code CRM system changes |  | Day 60
Integration | knowledge transfer |  | Day 60
Integration | System integration test |  | Day 60
Integration | Prototype review with business |  | Day 60
Integration | Business accounting matching completed |  | Day 90
Integration | User acceptance test |  | Day 90
Integration | CRM system go live |  | Day 90
Integration | Infrastructure Services Plans Defined |  | Day 91+
Integration | Perform site visit with Infrastructure and Facilities |  | Day 30
Integration | Engage the UL retired capital team to onboard the acquisition on apprpriate disposal process |  | Day 30
Integration | Review findings with business stakeholders |  | Day 60
Integration | Implement improvements to DR plan |  | Day 91+
Integration | Complete IT End of integration support matrix |  | Day 91+
Integration | Gather overall infrastructure integration requirements, conduct capacity analysis |  | Day 30
Integration | Create infrastructure BRD |  | Day 30
Integration | Define and execute Active Directory migration |  | Day 91+
Integration | Define and communicate estimate of IT infrastructure costs |  | Pre-Day 1
Integration | Complete Service Desk plan |  | Day 60
Integration | If services led acquisition, determine how to align infrastructure and data center components |  | Day 60
Integration | Review document storage solutions and determine migration plan. Review records retention policy. |  | Day 30
Integration | Ensure video conferencing requirements are included in BRD |  | Day 30
Integration | Get quote, confirm funding and order video conferencing equipment |  | Day 60
Integration | Install Video Conferencing |  | Day 91+
Integration | Publish interim SLA's and support model for the target |  | Day 30
Integration | Confirm decommision Plan for EOL products |  | Day 91+
Integration | Create an inventory of IT M&A application assets in Troux |  | Day 91+
Integration | Execute location and Facilities integration |  | Day 91+
Integration | Evaluate and implement DR solution |  | Day 91+
Integration | Perform assessment of DR capabilities |  | Pre-Day 1
Integration | Perform assessment of DR strategy and implementation |  | Day 60