## Sheet1
Rough Estimates of What we need from MOHRE Teams:
a. List of AI Projects | Suggested Inputs | MOHRE Stakeholders | Est. Hrs | Weeks | Total | Stakeholders | Totals
Approach: Obtain overview of Biz Architecture & Identify Initial List of Projects mapped to Risk & Value | Organization Chart, Product Portfolio, Services, List of Value Streams, Lifecycle Development | Business Portfolio Lead | 2 | 1 | 2 | Business Analyst / SME | 6
| Business Functions, Business Processes, Overview of Decision Making (hierachical, federated, criteria used, evaluation) | Business Analyst / SME | 4 | 1 | 4 | Business Operation Lead | 2
| Goals, Objectives, 'Metrics/KPIs | Business Operation Lead | 2 | 1 | 2 | Business Portfolio Lead | 10
| Systems Overview (Business, Integration Points, Services, Operations Flows) | IT Leader | 4 | 1 | 4 | Domain Architects | 4
| Corporate Glossary (Terms) | Domain Expert / SME | 0.5 | 1 | 0.5 | Domain Expert / SME | 0.5
| List of employee attributes (e.g. classifications, demographics, etc.), List of Performance Measures, List of gaps / concerns that are high priority (short term, long term) | Business Analyst / SME | 2 | 1 | 2 | EA Director | 8
b. Assessment of Short Term Opportunities | [5 empty] | Enterprise Architect | 24
Approach: Identify list of measures (features) to use for assessing operational AI opportunities. Identify 3-6 projects as quick wins for Stage 2 |  | Business Portfolio Lead | 2 | 4 | 8 | Finance (IT) | 16
|  | Finance (IT) | 2 | 4 | 8 | IT Leader | 4
|  | Enterprise Architect | 2 | 4 | 8 | Grand Total | 74.5
|  | Finance (IT) | 2 | 4 | 8
c. Draft Outline for Long Term Forward Plan
Approach: Draft outline covering AI vision for HR supported by a progression of projects that address horizontal & vertical concerns in the future. |  | EA Director | 2 | 4 | 8
|  | Enterprise Architect | 4 | 4 | 16
|  | Domain Architects | 1 | 4 | 4
Totals |  |  |  |  | 74.5
PLEASE NOTE: that the above tasks are overlapping and some run concurrently and therefore the each resources estimates are not linear and cumulative. Same resources may work on few concurrent tasks reducing the Net Ask from that individual.