## Actions Required
MetaModel Team: Actions Required
Priority | Activity | Task | Lead | ETC | Status | Comments
1. High | Admin | Get all team members to sign agreement by 12/10 | All |  | In Process
| Admin | Consolidate the teams into one MM Team | Jeff |  | Done
| Admin | Establish a set of milestones for the team | Jeff |  | Open
1. High | Admin | Get Marc Lankhorst and others signed up on website | All |  | In Process
| Admin | Jeff to revisit the 2-YR roadmap and update | Jeff |  | Open
| Admin | Jeff to setup actions required to track progress | Jeff |  | Done
| Admin | Review principles and assumptions with the team and then consider publishing alongside the charter. | All |  | Open
| Admin | Setup bi-weekly conference schedule for team | Jeff |  | Done
| Admin | Update the team charter per input from mentor and members | Jeff |  | In Process
| Inputs | Align MM with scenarios from Requirements Team, Information Mapping Team, Strategy Team, BPM Team | Jeff & Janice |  | In Process
| Inputs | Jeff & Janice touch base on the above mentioned ideas for INPUTS team | Jeff & Janice |  | Done
| Inputs | Need a process to align with BIZBOK Standards & other BIZBOK Teams | Jeff & Janice |  | In Process
| Inputs | need to address the term “scenario” so we don’t confuse it with business scenario. | Janice |  | Open
| Inputs | need to meet with Janice and talk about the right granularity for a given scenario and which scenarios we should address | Jeff & Janice |  | Open
| Inputs | Revisit Section 4 (contains the scenarios) determine if we need to reformat and/or supplement with a more formal structure (tbd) that would simplify our x-ref activities with the MM | Janice |  | Open
| Inputs | Setup discussion with BA Team (Janice) and Franz & Giovanni to suggest a few example relationships that we need to consider | Jeff |  | Open
| Modeling | Additional MMs include: UPDM, SPMS, and others |  |  | Open
| Modeling | Determine if we need a separate discussion for publishing a set of perspectives to support consumers of the MM |  |  | Open
| Modeling | Ensure the model aligns with current standards (UML) |  |  | In Process
| Modeling | need to address nomenclature for the relationships (mix of styles needs to be cleaned up). Adopt a convention and be explicit about it going forward. | All |  | In Process
| Modeling | Need to define how we are going to instantiate the relationships within the model. |  |  | In Process
| Modeling | need to send out the SPARX MM to the team | Peter G. |  | Done
| Modeling | one possible future scenario (pun intended) is to consider defining an ontology to accommodate a more adaptable set of relationships for the MM in the future | Jim R. |  | Open
| Modeling | revisit the structure of relationships and their directionality (need to be explicit and clear going forward) | Jim, Chalon, Llloyd |  | Open
| Modeling | setup a working session with team (walkthrough example put together by Chalon and Lloyd). Next week. | Chalon, Lloyd |  | In Process
| Modeling | Use one (or two) Scenarios to draft the approach for defining the "Lego Connection" concept that we discussed (connecting with one or more BA Models) | Jeff, Jim, Janice |  | Open
| Planning | Setup a plan to coordinate BA Guild response to RFP | Jeff, Jim |  | Open
| Planning | Setup discussion for team (reference Janice's slide 18 along with other lists) - establish a pipeline / backlog with prioritization scheme (Demand Mgmt process) | Janice |  | Open
| Planning | Team - review the current MM (diagram) and Appendix (Relationships) | All |  | In Process
| Planning | Team to review Section 5.1 of BIZBOK¨ GUIDE | All |  | In Process
| Planning | Team to review white paper published by Jim & Lloyd | All |  | In Process
| Publishing | Need to align the MM release cycle with publishing teams (** key point is to ensure the MM Governance ties into the larger release management process stewarded by the PMO for the BIZBOK) | Jeff, Alex, Janice |  | In Process
| Publishing | Update all references for the BIZBOK with the updated registered trademark | Jeff |  | Done
| Vendor Engagement | Coordinate call with vendors with Jim & Bill | Jeff |  | Open
| Vendor Engagement | Need to establish a vendor engagement process | Jeff |  | Open
| Vendor Engagement | Send a note to the BA Guild members and Vendor contacts about the upcoming meeting in Long Beach | Bill |  | Done
| Vendor Engagement | Setup a discussion with key vendors at the OMG to discuss publishing standards (includes 7 separate sets of documentation) | Jeff |  | Open
| Vendor Engagement | Touch base with Ramsay Millar (vendor touchpoint with Sparx) | Jeff |  | Done