## Purpose:

- Develop a core BAMM (Business Architecture Metamodel) with extensions to support common sets of scenarios as informed by other BIZBOK™ teams.

- Incorporate BAMM into the BIZBOK™ and provide practitioners with an explanation of the BAMM along with guidance for how to extend the BAMM and use it to optimize business architecture for an organization.

- Establish a Glossary of Terms used for Metamodeling, which is separate from the Terms used by practitioners (as found in the BIZBOK™).

- Provide a way to align Metamodeling terms with Terms used in the BIZBOK™ as well as Terms used in organizations.

- Provide a way to align the BAMM with other Metamodels using scenario-based extensions to the BAMM

- Support the OMG’s RFP for a BAMM and ensure the Guild’s BAMM is aligned with the OMG’s BAMM

- Collaborate with tool vendors to enable the business architecture community as well as other architecture communities who might develop and / or rely upon business architecture for developing solutions

## Key Stakeholders:

BIZBOK™ Teams

BIZBOK™ Editorial Board

OMG BAsig & Emerging BAMM Standard

Business Architecture Communities of Practice

Other Architecture Communities of Practice (including but not limited to IT Architecture)

Vendor Community supporting architectural modeling

## Scope:

OMG BAMM – Align with their emerging BAMM

Align BAMM terms with BIZBOK™ Glossary of terms

BIZBOK™ Section 5.1 - Define the concepts & associations used in the BAMM and align them to the prose used throughout the BIZBOK™

Includes the following:

Metamodel (entities & relationships)

Concise set of terms & relationships

Semantics (supporting different perspectives)

Commentary (describing the relationships)

Validated Scenarios captured by other BIZBOK™ teams

## Projects & Objectives:

Core Metamodel

- Provide input and guidance to the OMG for their RFP

- Align BIZBOK™ BAMM with OMG BAM

- High Level Metamodel (core entities & relationships)

- Develop a Metamodel Glossary leveraging existing terms from BIZBOK™

- Commentary & Instructions for building a Metamodel

Extended Metamodel(s) (note that we may have multiple variations given our standardization strategy)

- Conduct a review of the BIZBOK™ as input to the extended Metamodel

- Add adjacent entities & relationships to the Metamodel

- Add additional terms as the practice dictates

- Capture semantics and accompanying context

- Begin capturing scenarios from practitioners (this will run in parallel)

Expanded Metamodel

- Continue adding the following:

  - Incorporate business / IT mappings from BIZBOK™ Part 6

  - Adjacent entities, terms & relationships to the Metamodel

  - Terms (from the BIZBOK™ & beyond the BIZBOK™)

  - Semantics and accompanying context

- Continue adding scenarios from practitioners and organizations

- Continue enhancing the BIZBOK™ based on the evolution of the practical and scenarios, with continuing realignment within the Metamodel to reflect this practice based evolution.

## Organization:

### Core Team:

Jeffrey Wallk <jeffrey.wallk@enablingvalue.com>,

Jim Rhyne jrhyne@thematix.com

Jesse Leung jleung@mega.com

Alain Picard apicard@benchmarkconsulting.com

Chalon G Mullins chalon.mullins@earthlink.net

Lloyd Dugan lloyd@bpm.com

### Extended Team:

Jeffrey Wallk <jeffrey.wallk@enablingvalue.com>,

Jim Rhyne jrhyne@thematix.com

Jesse Leung jleung@mega.com

Alain Picard apicard@benchmarkconsulting.com

Chalon G Mullins chalon.mullins@earthlink.net

Lloyd Dugan lloyd@bpm.com

Darius.silingas@nomagic.com darius.silingas@nomagic.com

Franz Thiel franz.thiel@tridixx.com

Giovanni Traverso gt62it@outlook.com

Jelenaz Zdravkovic jelenaz@dsv.su.se

Neal McWhorter neal.mcwhorter@strategicvaluepartners.com

Marc Lankhorst <m.lankhorst@bizzdesign.nl>

### Mentor:

William Ulrich <wmmulrich.tsg@gmail.com>