## BA MM Roadmap
BIZBOK MetaModel Roadmap | [6 empty] | Assignments
Release Schedule | [6 empty] | Core - Jeff W |  |  |  | Group 1 - Jeff W | [5 empty] | Group 2 - Jeff C
| Detail | Type | Description | Status | Original ETC | v6/1 ETC | Jim | Lloyd | Chris A. | Chalon | Dave D. | Alaine | Serge | Brad | James | Frank K. | Adina | Chris M. | Philipp | Scott P. | Derek | Terry R.
BA MM (Core) | Core | Package | Capability Mapping | REVIEW | May | June | X | X | X | X
BA MM (Core) | Core | Package | Organization Mapping | Draft | May | June | X | X | X | X |  |  |  | X
BA MM (Core) | Core | Package | Value Mapping | REVIEW | May | June | X | X | X | X
BA MM (Core) | Core | Package | Information Mapping | Draft | May | June | X | X | X | X | [9 empty] | X | X
BA MM (Penumbra) - Phase 1 | Penumbra | Package | Business Strategy Mapping |  | Q2 | Q2 | X | [7 empty] | X
BA MM (Penumbra) - Phase 1 | Penumbra | Package | Initiative Mapping |  | Q2 | Q2 |  |  |  |  | X | [6 empty] | X
BA MM (Penumbra) - Phase 1 | Penumbra | Package | Product Mapping |  | Q3 | Q3 | [6 empty] | X |  |  |  |  | X |  |  |  | X
BA MM (Penumbra) - Phase 1 | Penumbra | Package | Stakeholder Mapping |  | Q2 | Q2 | [5 empty] | X
BA MM (Penumbra) - Phase 1 | Penumbra | Package | Policy Mapping |  | Q2 | Q2 | [7 empty] | X |  |  |  | X |  | X
BA MM (Penumbra) - Phase 2 | Oligaemia | Alignment | BPM and Management |  | Q2 | Q3 |  | X | [7 empty] | X | [5 empty] | X
BA MM (Penumbra) - Phase 2 | Oligaemia | Alignment | Case Management |  | Q2 | Q3 |  | X |  |  |  |  | X | [7 empty] | X
BA MM (Penumbra) - Phase 2 | Oligaemia | Alignment | Business Performance Mgmt. |  | Q3 | Q3 | [5 empty] | X |  |  |  | X |  |  |  |  | X | X
BA MM (Penumbra) - Phase 2 | Oligaemia | Alignment | Requirements Alignment |  | Q3 | Q3 | [7 empty] | X | [7 empty] | X
OMG Submission Packaging | MM (VDML) | Touchpoint | Value Delivery Modeling Language |  | Q2 | Q2 | X |  |  |  | X
OMG Submission Packaging | MM (BPMN) | Touchpoint | Business Process Model & Notation |  | Q3 | Q2 |  | X | [12 empty] | X | X
OMG Submission Packaging | MM (CMMN) | Touchpoint | Case Management Model & Notation |  | Q3 | Q3 |  | X | [12 empty] | X
OMG Submission Packaging | Initial Draft | Documentation | Overview Document with pictures |  | Q3 | Q3 |  |  | X | [5 empty] | X |  | X |  | X
OMG Submission Packaging | Initial Draft | Files & Artifacts | Metamodel Files |  | Q3 | Q3 |  |  | X | [5 empty] | X |  | X |  | X
OMG Submission Packaging | MM (DMN) | Touchpoint | Decision Model & Notation |  | Q4 | Q3 |  | X | [7 empty] | X
OMG Submission Packaging | MM (SBVR) | Touchpoint | Semantics of Business Vocabulary & Rules |  | Q4 | Q4 | X | [8 empty] | X
OMG Submission Packaging | MM (BMM) | Touchpoint | Business Motivation Model |  | Q4 | Q4 |  |  |  | X | [11 empty] | X
OMG Submission Packaging | Internal Review | Review | Document & MM Review (internal) |  | NOV | NOV | X | X | X | X
OMG Submission Packaging | MM (SMM) | Touchpoint | Structured Metrics Meta-model |  | Q4 | Q4 | [5 empty] | X | [7 empty] | X |  | X
OMG Submission Packaging | Open Group (MM) | Touchpoint | TOGAF Meta-Model |  | Q4 | Q4 |  |  |  | X | X | X
OMG Submission Packaging | Open Group (MM) | Touchpoint | ARCHIMATE Meta-Model |  | Q4 | Q4 |  |  |  | X | [6 empty] | X |  | X
| Master Draft | Touchpoint | (Leverage Bill's baseline text) |  | Q4 | Q4 | [7 empty] | X
OMG Submission Packaging | Initial Submission | Submission | Communication & Publishing |  | Q1 2018 | Q1 2018 | X | X |  | X
OMG Submission Packaging | OMG Review | Updates | Revisions |  | Q1 2018 | Q1 2018 | X | X |  | X | X | X | X | X | X | X | X |  | X | X | X | X
OMG Submission Packaging | Final Submission | Final Submission | Final Submission to OMG |  | Q1 2018 | Q1 2018 | X | X |  | X
KEY ROLES
| Model Librarian |  | Metamodel Packages & Version Mgmt. |  | ONGOING | ONGOING |  |  | X
| Packaging Librarian |  |  |  | ONGOING | ONGOING | [10 empty] | X
| Publishing |  |  |  | ONGOING | ONGOING | [8 empty] | X