## BA MM Roadmap
BIZBOK MetaModel Roadmap
Release Schedule |  |  |  |  | Assignments
| Detail | Description | Milestone | Timeline | Jim | Lloyd | Chris | Brad | Frank K.
BA MM (Core) | Core | Capability Mapping |  | 2016-09-01 | Draft
BA MM (Core) | Core | Organization Mapping |  | 2016-09-01 | Draft
BA MM (Core) | Core | Value Mapping |  | 2016-09-01 | Draft
BA MM (Core) | Core | Information Mapping |  | 2016-09-01 | Draft
BA MM (Penumbra) - Phase 1 | Phase 1 | Business Strategy Mapping |  | 2016-11-01 | Late
BA MM (Penumbra) - Phase 1 | Phase 1 | Initiative Mapping |  | 2016-11-01 |  |  |  | Draft
BA MM (Penumbra) - Phase 1 | Phase 1 | Product Mapping |  | 2016-11-01 |  |  | Late
BA MM (Penumbra) - Phase 1 | Phase 1 | Stakeholder Mapping |  | 2016-11-01 | Draft |  |  | Draft
BA MM (Penumbra) - Phase 1 | Phase 1 | Policy Mapping |  | 2016-11-01 |  |  | Late
BA MM (Penumbra) - Phase 2 | Phase 2 | BPM and Management |  | 2016-12-30 |  | Draft
BA MM (Penumbra) - Phase 2 | Phase 2 | Case Management |  | 2016-12-30 |  | X
BA MM (Penumbra) - Phase 2 | Phase 2 | Business Performance Mgmt. |  | 2016-12-30 |  |  |  |  | X
BA MM (Penumbra) - Phase 2 | Phase 2 | Requirements Alignment | x | 2016-12-30 |  |  | X
OMG Submission Packaging | Planning Timeline | Align with OMG Schedule |  | 2017-01-01
OMG Submission Packaging | MM (VDML) | Value Delivery Modeling Language |  | 2017-02-01
OMG Submission Packaging | MM (BPMN) | Business Process Model & Notation |  | 2017-02-01
OMG Submission Packaging | MM (CMMN) | Case Management Model & Notation |  | 2017-02-01
OMG Submission Packaging | Initial Draft | Overview Document with pictures | x | 3/1/2017+6mo
OMG Submission Packaging | Initial Draft | Metamodel Files | x | 2017-03-01
OMG Submission Packaging | MM (DMN) | Decision Model & Notation |  | 2017-03-01
OMG Submission Packaging | MM (SBVR) | Semantics of Business Vocabulary & Rules |  | 2017-03-01
OMG Submission Packaging | MM (BMM) | Business Motivation Model |  | 2017-03-01
OMG Submission Packaging | Internal Review | Document & MM Review (internal) |  | 2017-04-01
OMG Submission Packaging | MM (SMM) | Structured Metrics Meta-model |  | 2017-04-01
OMG Submission Packaging | Open Group (MM) | TOGAF Meta-Model |  | 2017-04-01
OMG Submission Packaging | Initial Submission | Communication & Publishing | x | 2017-05-01
OMG Submission Packaging | OMG Review | Revisions |  | 2017-08-01
OMG Submission Packaging | Final Submission | Final Submission to OMG | x | 2017-08-01
Vendor Engagement to be discussed in the next meeting (09-09-16)