## Slide 1: Guild – BAMM Team 2016 Plan
Proposal: Jeff Wallk
December 2015

## Slide 2: Outline
Supply Chain Vision
Key Artifacts
Engagement Model (internal)*
Engagement Model (external)*
Demand Planning
Quarterly Update Cycle
* Guild Perspective

## Slide 3: Supply Chain Vision
Thus far, the Guild BAMM Team has operated using a top down approach with the idea that what is produced will be adopted and /or consumed by standards organizations, vendors, and practitioners (business architects and any other architects).
This has proven an tough road and with the ongoing effort to promote the Guild’s perspectives for BA in OMG has distracted the team’s ability to achieve continuity and productivity has fallen off.
The purpose of a supply chain vision is to align the BAMM with the upstream and downstream value chain players.

## Slide 4: Supply Chain Vision
Demand Planning
Scenarios
Demand
Forecasting
BIZBOK
Teams
BAMM
Team
BAMM
Versions
Vendors
BA Practitioners
& Other Architects
Production
Plan
Component
Requirement
Version Management

## Slide 5: Supply Chain Vision
Why should we consider adopting this type of approach ?
  Aligns us with the value chain and the stakeholders we serve
  Ensures we are not developing artifacts that will not be adopted
  Establishes a much needed 360 feedback loop with stakeholders
  Builds a collaborative across the BIZBOK teams and stakeholders to create an integrated Demand Planning capability
  Fosters cooperation and improved communication with the vendor community
  Promotes the use of measures and business architecture to ensure all parties are aligned to address the needs of the customer

## Slide 6: Moving to a “Pull” Approach for Modeling
To further the move towards a customer-centric modeling approach, a portfolio of demand will be developed using a combination of scenarios (some of which are identified below as commonly occurring in businesses) and vendor outcomes (which ensure their revenue models are not disrupted while providing the MetaModel team & Tool team with direct access to the vendor community).
The starting point with the vendor outcomes is to agree on a common core for the Metamodel elements that aligns with existing Metamodels in use by vendors (and which are being used by their customers – Business Architects).

## Slide 7: Establishing Release Management
Once we agree on the core elements for the Metamodel, we can begin working with the BIZBOK Tool team and the Vendors to agree on a publishing mechanism for enabling key features:
  Functionality needed by the practitioners of business architecture to perform their jobs, as well as the
  Metamodel artifacts (see next slides) that support the current and future needs of business architects (which we realize is an evolving discipline with increasing opportunities for integration with other disciplines).
Note: Version Management & Change Control will require careful coordination and will need to be driven by the Vendor Community and supported by the Metamodel & Tool teams.

## Slide 8: Key Artifacts - Glossary
The Guild BAMM Team has struggled with progress due to distractions and challenges in overcoming terminology. Terms will come and go as they are more fluid in nature and are subject to interpretation based on perspectives.
Moving forward, we need to align on the HOW not the WHAT regarding the use of terms. The goal is to establish a simple but extendible glossary & semantic mapping capability. The BAMM team needs it as do the vendors and architecture practitioners (all disciplines).

## Slide 9: Key Artifacts - MetaModel
Leverage the MOF standard for defining Metamodels, which is also aligned with OMG.
Address core domains (minimally) for strategy, initiative, stakeholder, product, and capability.
Incorporate touch points to other architecture and professional disciplines (some of which are defined in OMG).
Design for flexibility and adaptability to address:
  Perspectives
  Change & Version Management

## Slide 10: Key Artifacts - Relationships
Relationships need to specify cardinality
Relationships need to be individually defined, tied to a scenario (see next slide) and x-ref to the Metamodel.
The Metamodel will only reference a single line between concepts, however each line will have a 1:M relationship to specific instances of relationships.
Each relationship instance may address one or more perspectives and scenarios. *
  * This is where we will need to align with the vendor community to ensure we can agree on a consistent approach to support release management

## Slide 11: Key Artifacts - Scenarios
Define a subset of commonly referenced scenarios found in businesses. Below is a starting list:
Investment Analysis
Shift to Customer Centric Business Model
Merger & Acquisition Analysis
New Product/Service Rollout
Globalization
Business Capability Outsourcing
Supply Chain Streamlining
Divestiture
Regulatory Compliance
Change Management
Operational Cost Reduction
Joint Venture Deployment

## Slide 12: Modeling Principles

## Slide 13: Modeling Principles
Mechanism for integration with other models
Submissions shall provide a mechanism for integrating a business architecture model instantiated from the submitted meta-model with external models. Submissions must meet at least the following two conditions:
  Integration with other models instantiated from an OMG MOF-based meta-model
  Integration with other models whose elements are uniquely identified by an Uniform Resource Identifier (IETF RCC 3986)
An example of such a mechanism would be the incorporation in a meta-model submission of “proxy” elements, whose sole purpose is to represent an element in an external model, and which would contain an identifier, which on presentation to a software program capable of working with the external model, would allow that software program to find and access 1 or 0 elements in that model.

## Slide 14: Modeling Principles
Element properties
All model elements instantiable from the proposed meta-model must have a label and a description and an ability to be tagged with a simple property-value list.
Model Reuse
In order to facilitate model reuse, meta-model submissions must provide for both abstract and concrete versions of model elements. Abstract model elements should be reusable across businesses of the same type, while concrete model elements should represent parts of a specific business. Concrete model elements shall be associated with at most one abstract model element.

## Slide 15: Modeling Principles
Model representation target
The models instantiated from the proposed meta-model shall represent a business or a set of related businesses (e.g. a virtual enterprise) or a set of similar businesses (e.g. competitors in a marketplace) or a set of similar, related businesses. The term “business” is defined as in https://en.wikipedia.org/wiki/Business.

## Slide 16: Content requirements

## Slide 17: Content Requirements
Capability modeling
The submitted meta-model shall be capable of instantiating a capability model such that capabilities may be arranged in a hierarchy (a singly rooted tree whose nodes have at most one parent).
Value modeling
The submitted meta-model shall be capable of instantiating models representing sequences of value creating activities, together with representations of the value items created and the stakeholder roles who receive those value items.
A value creating activity shall be associated with zero or more capabilities in an associated capability model of the same business or set of businesses.

## Slide 18: Content Requirements
Organization modeling
The submitted meta-model shall be capable of instantiating models of organization structures of various types, including command and control structures and collaboration structures. Stakeholder roles from value models shall be included in organization models. Organization models shall include roles representing direction and control of capabilities and value creating activities.

## Slide 19: Content Requirements
Information modeling
The submitted meta-model shall be capable of instantiating models of information, and of associations of information model elements to capabilities representing business components which use and create the information. The instantiated models should be capable of representing the aggregation of information and the derivation of information from other information