### Agenda:

- Attendees: Jeff, Paula

### Agenda:

- Review initiative with Paula

- Review Meta Phrases worksheet

- Discuss next steps with deliverables & timelines

- Actions Required

Reference: Metamodel Folder in Google Docs

### Minutes:

- Reviewed the background and approach for the project team

- Discussed the metamodel Paula provided (uploaded to folder)

- Reviewed the progress for the Metaphrase capture (spreadsheet in folder)

- Discussed the need to leverage existing metamodels (in BizBok & from practitioners like Paula, Steffan, and others) that are based on the BizBok for our initial footprint

- Jeff will review Paula’s model and provide comments in the folder (suggest all team members follow suit)

- Noted that we’re already at the end of March and have a hard cutoff for the next release of the BizBok by April 30th, so we’re going to have to leverage the in-practice metamodels and align with the existing metamodel in the BizBok (which is also uploaded in the team folder) so we can agree on an initial footprint.

- The team will need to continue working on the bottom up approach in parallel to this top-down / alignment approach so we can make our deadline.

- Please reference the updated deck, which Bill uploaded to the Community location in BA Guild’s website. (I uploaded a copy to our team folder for your reference).  Note the additional names of participants).

### Actions Required:

- Jim will draft a portion of the metamodel and document the steps as a pilot for the team in 2 weeks.

- NO Meeting next Friday (Jeff out on vacation) Everyone needs to get their actions required completed.

- Everyone needs to review the existing models uploaded to the team folder (see link above)

- Everyone needs to review the team charter (also uploaded to the team folder)

- See cross-reference table below for this week’s assignments.

| Domains (practice areas of BizBok) | Owners | Status |
| --- | --- | --- |
| Business Strategy | Jeff | done |
| Capability Mapping | Jeff | done |
| Organization Mapping | Damian (Simon) |  |
| Value Mapping | Damian (Bob) |  |
| Information Mapping | Neal (Simon) |  |
| Product Mapping | Neal (Eric) |  |
| Stakeholder Mapping | Simon |  |
| Initiative Mapping | Simon |  |