Attendees:

Jeff Wallk

Jeff Crites

Bill Ulrich

Alain Picard

Scott Parkin

Adina Aldea

Serge Behar

Derek Renouf

(Dennis & Stephen)

Regrets:

Lloyd Dugan

Jim Rhyme

Chalon Mullins

Chris Armstrong

Dave Dugal

Brad Jeter

Frank Kowalkowski

Phillipp Kutter

James Corcoran

Agenda:

- Introductions of new members

- Discuss Roadmap

- Update on OMG RFP

- Guild Summit Update

==========================================

Minutes:

- Team Members:

  - Adina Aldea - BizzDesign

  - Jeff Wallk – co-lead

  - Jeff Crites – co-lead - FedEx

  - Alain Picard - Benchmark

  - Scott Parkin – Holocentric

  - Derek Renouf – Holocentric

  - Bill Ulrich – Guild / TSG

  - Terry Roach – Capsicum

  - Serge Behar – Quebec Consultant

  - Dave Duggal – Enterprise Web

  - Jim Rhyne / Thematix

  - Chris Armstrong / APG

  - Frank K. - KCI

  - Lloyd Dugan – BPM.com

  - Chalon Mullins – Kaiser

  - Brad Jeter – Boeing

  - Philipp Kutter - Accenture

  - James Corcoran – USAA

- Roadmap for BIZBOK

  - Dennis (Roadmap/Editor)

- Team Mentor

  - Stephen Marshall – IBM – mentor

- Bill Updates and Key Dates:

  - Finalize core domain packages next 30 days

  - Finalize extended domains by mid-Q3

  - Finalize interdisciplinary / OMG related standards touchpoints by mid-Q4

  - Draft RFP ongoing Q2-end Q4

  - Refine deliverables Dec. 2017 - Feb. 2018

  - Submit Letter of Intent for all submitters Sept 10th

  - Final submission date Feb. 29, 2018

- Presentations in Reston March 19, 2018

- Review of key deliverables

  - Packages – model artifacts

  - Packaging – alignment to other Metamodels

- Need to wrap up all the draft work by EOY so we can review & fine tune in first month of 2018

- While the minimum submission for RFP response only requires the Capability package, the Guild will be submitting a robust set of packages per the roadmap

- Meetings will be setup to accommodate two separate regions of time zones

- An additional monthly meeting will be setup with the Core Team to review deliverables (return with feedback or approve)

- Will need some of the team members to step up into key roles

  - Model Librarian – version & configuration management

  - Packaging Librarian – versioning the packaging for the RFP

  - Publishing – drafting & versioning of BIZBOK & White Papers

- Jeff & Jeff will review collaboration tools and content within the team and across BIZBOK teams

- Jeff & Jeff will schedule and drive the meetings

  - Jeff W – Group 1

  - Jeff C – Group 2

  - Jeff W – Core Team (includes Jeff C)

Actions Required:

- (All) Review Part 6 of the RFP

- (Jeff & Jeff) minutes & setup of meetings for teams

- (Jeff & Jeff and Dennis) Align on Roadmap details

- (Jeff & Jeff) reach out to Chris Armstrong for a solution to manage issues

- (Jeff & Jeff) send out Roadmap with divide and conquer on deliverables

- (All) respond with approvals / changes to Roadmap work alignment