### Agenda:

- Attendees: Jeff, Simon, Jim R, Alain, Damian, Steve H.

### Agenda:

- Review Metamodel Plan v2

- Agree on starting point for drafting the model

- Agree on deliverables & timelines

- Assign individuals to work streams (5 teams with specific roles - ref Plan v3)

Reference: Metamodel Folder in Google Docs

### Minutes:

- Note that the charter was updated & reviewed by the mentor.  Assume everyone has read this and we’re good to go.

- We’re starting to amass a fair amount of collateral, so Smon started to consolidate some of the materials in folders (examples now have sample models for folks review).  I took Simon’s lead and organized all the materials into folders.

- Note: Please reference the Phase 1 for all artifacts related to the 4/30 deliverable

- We reviewed the work from Franz Theil’s model. Lot of good information. We also reviewed the work from Damian’s model, which covers similar territory from Franz and went a bit further.  The core team felt we need to incorporate a formal process that provides traceability from the model back to the inputs (BIZBOK being the initial input for now).

- So, we agreed to use a stepwise approach where first document the Inputs (Section 2 of the BIZBOK) and then use that to draft the initial model. The model will contain core & non-core entities (adjacent entities and/or subsequent levels of categorization). Once the model is drafted, we’ll review and identify the core entities. From there, the modeling team (Damian for now) will “filter” the model and we will produce the final draft model.

- Damian will also incorporate the Input into the glossary (part of the modeling tool - using SPARX for now) and produce the accompanying glossary as part of a final deliverable for the Modeling team and Glossary team.

- The Input worksheet will be published into the BIZBOK in the appendix and used as reference to support the model and glossary in Section 2.

- There’s a lot of work in a short amount of time for the team, so we’re going with the attendees for the call to staff the teams for Phase 1.

- The work streams will be helpful once we start pushing into Phase 2 as that promises to be a larger scope of work and we’ll need more participation from the team going forward.  Start thinking about which teams you want to participate in for that effort, since it will launch after we complete the work for Phase 1 (later in May after BIZBOK editing is completed).

### Actions Required:

- Simon to work with Damian on Input Capture worksheet (done)

- Jeff to draft updated plan v3 (done)

- Jeff to clean up docs & folders (done)

- Jeff, Damian, Simon, Jim to update Input Catpure with their assignments (see plan v3)

- Jeff to schedule call for next week 4pm CT (Input Review)