### Agenda:

- Attendees: Jeff, Simon, Paula, Neil, Damian, Steve H.

### Agenda:

- Team Updates:  Inputs, Modeling, Glossary, Publishing

- Future Planning

Reference: Metamodel Folder in Google Docs

### Minutes:

- The Inputs Team are about 80% complete with the updates to the metaphrases.  Jeff completed the bulk of the inputs for the team. Damian completed his inputs and just needs to upload them to the worksheet.

- The inputs represent a portion of the BIZBOK, so it’s a partial representation of the relationships that may exist in the BIZBOK. The terms that we captured from the BIZBOK may be further abstracted in future versions of the Glossary once the workgroup revisits the definitions and terms as part of a modeling rationalization exercise.

- The Modeling Team is expected to complete the draft model by end of the weekend.

- We discussed the need to pursue a traditional model in the next release of the BIZBOK, which could be used by practitioners as a reference model.

- We discussed the idea of drafting alternate views of the model as it begins to grow in complexity.  Perhaps we would continue to publish the high level model (conceptual view) with the core subject areas in section 2.1 of the BIZBOK and draft separate views (logical model) for each subject area.

- We will use scenarios to inform the model and identify gaps with the BIZBOK and the Glossary.  The Metamodel will continue to align with the BIZBOK, but it will not be confined to the BIZBOK as it is in the initial release. The gaps will need to be shared with a governance team to determine how best to incorporate any changes to the BIZBOK (terms and relationships).

- We may call a meeting on 4/30 to review the artifacts prior to submission.

- In the meantime, we’ll need the Review Team to scan the work from the Publishing Team and make sure the updates for the BIZBOK are ready to go.

### Actions Required:

- Damian to upload his updates to the Input Capture worksheet

- Jim to complete his updates to the Input Capture worksheet

- Jeff to draft section 2.1 updates for the BIZBOK v4.0 (done)

- Damian to complete draft of the Metamodel

- Damian to provide draft of the Glossary

- All available parties to review the draft for section 2.1 (in the google docs folder)